## Risk Register
Asset ID | Asset Name | Asset Type | Confidentiality | Integrity | Availability | Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Existing Controls | Treatment Plan | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Residual Risk Level | Owner | Status | Review Date
AST-001 | Employee Laptops | Endpoint | High | Medium | Medium | R-001 | Phishing email leads to compromised employee credentials | Cybersecurity | 4 | 4 | 16 | Critical | Email filtering, security awareness training | Enforce MFA org-wide; run quarterly phishing simulations | 2 | 3 | 6 | Medium | IT Security | In Progress | 2026-10-01
AST-002 | Customer Database | Database | High | High | High | R-002 | SQL injection vulnerability in customer-facing web application | Cybersecurity | 3 | 5 | 15 | Critical | Web Application Firewall (partial coverage) | Implement parameterized queries; expand WAF coverage; run penetration test | 1 | 5 | 5 | Medium | Application Security | Open | 2026-09-15
AST-003 | Company File Server | Server | High | Medium | High | R-003 | Data at rest is not encrypted | Cybersecurity | 3 | 5 | 15 | Critical | None currently — data stored in plaintext on disk | Implement AES-256 encryption for all data at rest | 1 | 5 | 5 | Medium | IT Security | Open | 2026-09-30
AST-004 | Cloud Storage Bucket | Cloud Storage | High | High | Medium | R-004 | Cloud storage bucket misconfigured with public access | Cybersecurity | 3 | 5 | 15 | Critical | Manual quarterly configuration review | Deploy automated Cloud Security Posture Management (CSPM) tool | 1 | 5 | 5 | Medium | Cloud Engineering | In Progress | 2026-08-15
AST-005 | HR / Payroll System | Application | High | High | Medium | R-005 | Insider threat: unauthorized access to payroll and PII data | Compliance / Legal | 2 | 5 | 10 | High | Role-based access control (RBAC) | Implement quarterly access reviews and audit logging | 1 | 4 | 4 | Medium | HR / IT | Mitigated | 2026-12-01
AST-006 | Corporate Network | Network | Medium | Medium | High | R-006 | DDoS attack causes public service outage | Operational | 2 | 4 | 8 | Medium | Basic perimeter firewall | Subscribe to managed DDoS protection service | 1 | 3 | 3 | Low | Network Operations | Open | 2026-10-30
AST-007 | Privileged User Accounts | Identity | High | High | Medium | R-007 | Multi-factor authentication not enforced on privileged/admin accounts | Cybersecurity | 4 | 5 | 20 | Critical | Password complexity policy only | Enforce MFA for all privileged and administrative accounts | 1 | 5 | 5 | Medium | IT Security | Open | 2026-09-01
AST-008 | Vendor Management Platform | Third-Party System | High | Medium | Low | R-008 | Third-party vendor processes customer data without a signed DPA | Third-Party / Vendor Risk | 2 | 5 | 10 | High | Informal vendor review at onboarding | Require signed Data Processing Agreement before data access is granted | 1 | 3 | 3 | Low | Procurement / Legal | In Progress | 2026-09-01
AST-009 | Backup Infrastructure | Infrastructure | Medium | High | High | R-009 | Backup and disaster recovery plan exists but has never been tested | Business Continuity / Disaster Recovery | 2 | 5 | 10 | High | Automated nightly backups (untested restore) | Run quarterly DR test and document a formal recovery runbook | 1 | 4 | 4 | Medium | IT Operations | Open | 2026-11-01
AST-010 | Company-Issued Laptops | Endpoint | High | Medium | Medium | R-010 | Lost or stolen laptop with unencrypted local storage | Cybersecurity | 3 | 4 | 12 | High | Device encryption policy exists but is not enforced | Enforce full-disk encryption via MDM on all endpoints | 1 | 3 | 3 | Low | IT Operations | Open | 2026-10-15
AST-011 | SaaS Applications | Application | Medium | Medium | Medium | R-011 | Shadow IT: employees using unapproved SaaS tools with company data | Compliance / Legal | 4 | 3 | 12 | High | None | Deploy SaaS discovery tool; enforce acceptable use policy | 2 | 2 | 4 | Medium | IT Governance | Open | 2026-09-20
AST-012 | Server Room | Physical Facility | Low | Low | Medium | R-012 | Unauthorized physical access to server room | Physical | 2 | 3 | 6 | Medium | Keycard access control | Add biometric access control and maintain a visitor log | 1 | 2 | 2 | Low | Facilities | Mitigated | 2027-01-01
AST-013 | Corporate Email System | Communication | Medium | Medium | Medium | R-013 | Business email compromise / executive impersonation fraud | Cybersecurity | 3 | 4 | 12 | High | Basic spam filtering | Enforce DMARC/DKIM/SPF; run executive-targeted phishing training | 1 | 3 | 3 | Low | IT Security | In Progress | 2026-09-10
AST-014 | Financial Reporting System (ERP) | Application | High | High | Medium | R-014 | Segregation of duties not enforced for financial transaction approval | Financial | 2 | 4 | 8 | Medium | Manual monthly review by finance manager | Implement segregation-of-duties controls within the ERP system | 1 | 3 | 3 | Low | Finance / Internal Audit | Open | 2026-11-15
AST-015 | Employee Offboarding Process | Process | Medium | Low | Low | R-015 | Terminated employees retain access to systems after departure | Compliance / Legal | 3 | 4 | 12 | High | Manual offboarding checklist | Automate deprovisioning by integrating IAM with the HRIS | 1 | 3 | 3 | Low | IT / HR | Open | 2026-10-05
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low
[11 empty] | 0 | Low |  |  |  |  | 0 | Low

## Legend & Instructions
GRC Risk Register — Starter Kit
This register comes PRE-FILLED with 15 common organizational risks, already scored, so
you can see exactly how a finished risk register looks and reads before adding your own.
COLUMNS EXPLAINED
Asset ID / Asset Name / Asset Type — the system, data, or process the risk applies to.
Confidentiality / Integrity / Availability (CIA) — how sensitive this asset is on each of the
three classic information security dimensions (High/Medium/Low). This tells you WHY a risk
to this asset matters — e.g. a High-Confidentiality asset means a breach is especially costly.
Risk ID / Risk Description / Category — what could go wrong, and what kind of risk it is.
Likelihood (1-5) / Impact (1-5) — your judgment of how likely this is, and how bad it would be.
Risk Score / Risk Level — CALCULATED AUTOMATICALLY (Likelihood x Impact). Do not type into these.
Bands: 1-3 Low, 4-8 Medium, 9-14 High, 15-25 Critical.
Existing Controls — what's already in place today to reduce this risk.
Treatment Plan — the additional action that will further reduce the risk.
Residual Likelihood / Residual Impact — your estimate of Likelihood/Impact AFTER the Treatment
Plan is fully implemented.
Residual Risk Score / Residual Risk Level — CALCULATED AUTOMATICALLY, same formula as above,
applied to the residual numbers. Compare this to Risk Level to show a control's real effect.
Owner / Status / Review Date — who is accountable, where it stands, and when to revisit it.
HOW TO USE THIS AS A FRESHER
1. Read through the 15 pre-filled example risks first — they cover the most common risk types
(phishing, unencrypted data, weak access control, vendor risk, physical security, etc.)
and show realistic Likelihood/Impact judgments and Treatment Plans.
2. When you join a real organization, replace them (or add to them) with risks specific to
that company's actual assets and systems — the structure and formulas stay the same.
3. Status uses a dropdown: Open / In Progress / Mitigated / Accepted / Closed.
4. CIA and Likelihood/Impact fields are dropdowns too — just click and select.
5. Review Date turns RED automatically if it's overdue and Status isn't Closed/Mitigated.
6. See the Dashboard tab for a live summary of all risks by level, status, and CIA exposure.

## Dashboard
Risk Register Dashboard
By Risk Level
Risk Level | Count
Critical | 5
High | 7
Medium | 3
Low | 0
By Status
Status | Count
Open | 9
In Progress | 4
Mitigated | 2
Accepted | 0
Closed | 0
By Confidentiality Rating
Confidentiality | Count
High | 9
Medium | 5
Low | 1
Overdue Reviews (past due, not Closed/Mitigated)
Count | 0